## EIC 2015
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.03.2015)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 |  | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | Work completed | 5.82 |  | 3.82
Work likely to be enhanced upto 6.15 crs
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | work completed | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 |  | 23.1315 | Agreement Terminated | 22.03 | 72.3% | work completed | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 |  | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | work completed
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 |  | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | work completed
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 |  | 4.24 |  | 4.04 | 100% | Work completed. Building hand over
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 |  | 2.1 |  | 2.28 | 98% | work completed .building hand over
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2.2995 | Completed except P.C. | 2.19 | 100% | Work completed | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 85% | work completed
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 |  | 9.408 | 2010-02-15 | 8.96 | 80% | 1.work completed building hand over. 2. Only officer club completed upto 40% and to be completed within two months. | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 |  | 3.6645 | 31 Jan.2010 | 3.04 | 100% | work completed | 1.07
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 |  | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | work completed | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | work completed | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 |  | 4.7775 | 31.01.2010 | 4.55 | 100% | work completed | 3.48
| TOTAL | 64.72 | #REF! | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 |  | 63.46 |  | 60.27
| Supervision Consultancy Charges | [15 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [15 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency. Now work completed.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work comp
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.01 | 0.03 | 0.04 | 1.09 | 1.09 | 5.12.2010 | 22.96 | 100% | Work completed in all respect on dated 20.12.2013 and CIPET building handed over to client department on dated 28.02.2014
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | Work completed
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
PGRC,Jind
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 16.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0 | 0 | 0 | 5.54 | 5.54 |  | 24.13 | 100% | Overall ProgressReport Mess Block- Completed in all respect. Hostel Block Completed in all respect except one finishing coat and fixed glass.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota s
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 | 1.24 |  | 16.10.2013 | 15.02.2014 31.03.2014(revised) | 0 | 0 | 0 | 0 | 0 | 0.44 | 44.04 | 0 | 0.95 |  | 0 |  | 0.95 |  | Work completed
BPSMV,Sonepat
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and occupied by university authorities on 01.11.2014.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 90% work has been completed and wooden joinery completed.Paintaing and electrical and public health works are in progress and likely to be completed by 31.03.2015.The progress of work hampered due to non receipt of funds from university in time.
Academic Staff Hostel 78% work has been completed.The balance works of flooring ,palstering wooden,joinery,Electrical and public health works is in progress and likely to be completed by 31.03.2015. The progress of work hampereed due to non receipt of funds from university in time. Reaseach Scholar Hostel 80% wo
Hostel for Degree college (SINGLE STOREY):- 95% work has be3n completed. The balance work of paintaing , wooden joinery,Electrical & public health
Health Department
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Work allotted democration of alignment of building ,removing of tress, electric poles ,sewer line is in progress
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | Revised Admoinistrative approval of the work amounting of Rs. 5.00 crore has been acorded vide additional chief secretary to Govt.haryana Health Dept.vide no.20/59/2011-5HBIII dated 24.12.2014 whereas agreement of the work with the contractor is of Rs.549.42 lacs.S.E Rewari circle rewari circle rewari has already requested to ED HSRDC Panchkula vide letetr No.577 dated 30.01.2015 that permission may kindly be given to execute the work upto agreement amount as the revised estimate is under process and the same will be submitted shortly to get the revised .Administrative approval from the Health department.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | 25.22 | 0.98 | 8.98 | -7.43
131.901

## march 2015
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.01.2015)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month Jan | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
1 | Construction of varius building at DCRTPP Colony Yamunanagar (Non residential) Agreement amount RS.542.81 lacs | 64.73 | 5.43 | 8.37 | 17.04.2008 | 16.02.2009/ 31.11.2013 | 0 | 0 | 0 | 1.42 | 1.56 | 0.75 | 0 | 0 | 0 |  | 3.72 |  | 9.30 overall 3.72 only in this office | 95% | 1.Works completed. Building hand over. 2.Only officer club completed upto 40% and to be completed within two months.
2 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work comp
PGRC,Jind
a | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0.2 | 0 | 0.2 | 6.78 | 4.72 |  | 4.5 | 95% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) R.C.C. slab, and brick work completed iii) 100% cement plaster completed. Iv) 85% Grid slab laid completed. V) 65% flooring completed vi) 95% unistone unibrick cladding completed.External plaster is in progress. 2nd storey i) 100% RCC slab & brick work completed.External plaster is in progress ii) 95% cement plaster completed. iii) 95% Unistone unibrick cladding completed. external plaster is in progress. 3rd storey i)Slab completed & 95% brick work completed. ii) 75% flooring completed.80% plaster work completed and balance work is in progress. iii) 95% unistone unibrick cladding completed. External plaster is in progress. 4th stroey. i)95% slab brick & Plaster work completed. ii) 75% flooring completed. iii) 95% Unistone unbrick cladding completed. External plaster is in progress. B) progress up to expansion joint. Complete in all respect.) 2nd storey-complete in allrespect.Final touching of point is in progress. iii)3rd storey-Complete in all respect .Final touching of paint is in progress. 4th storey Complete in all respect .Final touching of paint is in progress. iC) progress upto Next expansion joint. Ist Storey RCC slab ,brick work & Plaster completed.75% grid slab/ flooring completed. ii) 2nd storey-Slab completed.Brick work & plaster work completed.75% flooring completed. iii) 3rd stprey- Slab completed ,95% brick work & Plaster work completed & 75% flooring completed. IV 4th storey-95% slab ,brick work & plaster work completed.75% flooring completed,casting of column are in progress.
3 | BPSMV,Sonepat
a | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.62 | 0 | 0.62 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and occupied by university authorities on 01.11.2014.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 90% work has been completed and wooden joinery completed.Paintaing and electrical and public health works are in progress and likely to be completed by 31.03.2015.The progress of work hampered due to non receipt of funds from university in time.
Academic Staff Hostel 78% work has been completed.The balance works of flooring ,palstering wooden,joinery,Electrical and public health works is in progress and likely to be completed by 31.03.2015. The progress of work hampereed due to non receipt of funds from university in time. Reaseach Scholar Hostel 80% wo
| Health Department | [19 empty] | Hostel for Degree college 95% work has been completed.The balance work of paintaing wooden joinery Electrical & public health works are in progress and likely to be completed by 31.03.2015.The progtess of work hampered receipt of funds from university in time.
a | Construction of additional block at district Hospital Panipat | 43 | - | [9 empty] | 0 | 0 | [6 empty] | Work allotted democration of alignment of building ,removing of tress, electric poles ,sewer line is in progress
b | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.33 | 0.08 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 80% | Revised Admoinistrative approval of the work amounting of Rs. 5.00 crore has been acorded vide additional chief secretary to Govt.haryana Health Dept.vide no.20/59/2011-5HBIII dated 24.12.2014 whereas agreement of the work with the contractor is of Rs.549.42 lacs.S.E Rewari circle rewari circle rewari has already requested to ED HSRDC Panchkula vide letetr No.577 dated 30.01.2015 that permission may kindly be given to execute the work upto agreement amount as the revised estimate is under process and the same will be submitted shortly to get the revised .Administrative approval from the Health department.
c | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | #REF! | 0.98 | 8.98 | -7.43
131.901

## jan 2015
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.01.2015)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 |  | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | Work completed | 5.82 |  | 3.82
Work likely to be enhanced upto 6.15 crs
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | work completed | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 |  | 23.1315 | Agreement Terminated | 22.03 | 72.3% | work completed | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 |  | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | work completed
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 |  | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | work completed
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 |  | 4.24 |  | 4.04 | 100% | Work completed. Building hand over
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 |  | 2.1 |  | 2.28 | 98% | work completed .building hand over
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2.2995 | Completed except P.C. | 2.19 | 100% | Work completed | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 85% | work completed
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 |  | 9.408 | 2010-02-15 | 8.96 | 80% | 1.work completed building hand over. 2. Only officer club completed upto 40% and to be completed within two months. | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 |  | 3.6645 | 31 Jan.2010 | 3.04 | 100% | work completed | 1.07
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 |  | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | work completed | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | work completed | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 |  | 4.7775 | 31.01.2010 | 4.55 | 100% | work completed | 3.48
| TOTAL | 64.72 | #REF! | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 |  | 63.46 |  | 60.27
| Supervision Consultancy Charges | [15 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [15 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency. Now work completed.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work comp
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.01 | 0.03 | 0.04 | 1.09 | 1.09 | 5.12.2010 | 22.96 | 100% | Work completed in all respect on dated 20.12.2013 and CIPET building handed over to client department on dated 28.02.2014
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | Work completed
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
PGRC,Jind
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 16.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0 | 0 | 0 | 5.54 | 5.54 |  | 24.13 | 100% | Overall ProgressReport Mess Block- Completed in all respect. Hostel Block Completed in all respect except one finishing coat and fixed glass.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota s
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 | 1.24 |  | 16.10.2013 | 15.02.2014 31.03.2014(revised) | 0 | 0 | 0 | 0 | 0 | 0.44 | 44.04 | 0 | 0.95 |  | 0 |  | 0.95 |  | Work completed
BPSMV,Sonepat
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and occupied by university authorities on 01.11.2014.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 90% work has been completed and wooden joinery completed.Paintaing and electrical and public health works are in progress and likely to be completed by 31.03.2015.The progress of work hampered due to non receipt of funds from university in time.
Academic Staff Hostel 78% work has been completed.The balance works of flooring ,palstering wooden,joinery,Electrical and public health works is in progress and likely to be completed by 31.03.2015. The progress of work hampereed due to non receipt of funds from university in time. Reaseach Scholar Hostel 80% wo
Hostel for Degree college (SINGLE STOREY):- 95% work has be3n completed. The balance work of paintaing , wooden joinery,Electrical & public health
Health Department
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Work allotted democration of alignment of building ,removing of tress, electric poles ,sewer line is in progress
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | Revised Admoinistrative approval of the work amounting of Rs. 5.00 crore has been acorded vide additional chief secretary to Govt.haryana Health Dept.vide no.20/59/2011-5HBIII dated 24.12.2014 whereas agreement of the work with the contractor is of Rs.549.42 lacs.S.E Rewari circle rewari circle rewari has already requested to ED HSRDC Panchkula vide letetr No.577 dated 30.01.2015 that permission may kindly be given to execute the work upto agreement amount as the revised estimate is under process and the same will be submitted shortly to get the revised .Administrative approval from the Health department.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | 25.22 | 0.98 | 8.98 | -7.43
131.901

## ongoing works 2015
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.03.2015)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2015-16 |  |  | Expenditure upto 31.03.15 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month March | Cumulative during 2015-16
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
1 | Construction of varius building at DCRTPP Colony Yamunanagar (Non residential) Agreement amount RS.542.81 lacs | 64.73 | 5.43 | 8.37 | 17.04.2008 | 16.02.2009/ 31.11.2013 | 0 | 0 | 0 | 1.42 | 1.56 | 0.75 | 0 | 0 | 0 |  | 3.72 |  | 9.30 overall 3.72 only in this office | 95% | 1.Works completed. Building hand over. 2.Only officer club completed upto 40% and to be completed within two months.
2 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 3.4 | 0.65 | 4.05 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013. |  | -2.11 | 7.21 | -6.28
Conevention centre The balance civil work stands allotted. The slab of 3rd floor has been laid 92% . Work of Kotastone flooring complete.85% of plastering work is completed. The fabrocation work of truss has been completed & the truss in workshop area has been launched.91% Brick work completed and balance in progress. Electrical , fire fighting and public health work is in progress. Tender for electrical work , HVAC work, Audio visual work,acoustics etc.could not be invited by EE. Electrical Division ,Karnal because the sope of work has not been finalized by the university authorities and the tender of the same will be floated after that.Against deposit of 41.45 crores an expenditure of 41.66 crore has been incurred upto Febuary, 2015 therefore further progress of the work has stalled for want of funds from the University. Overall Physical progress 45% of the remaining work.
PGRC,Jind
a | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0.2 | 0.46 | 0.66 | 6.78 | 4.72 |  | 4.5 | 95% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) R.C.C. slab, and brick work completed iii) 100% cement plaster completed. Iv) 85% Grid slab laid completed. V) 65% flooring completed vi) 95% unistone unibrick cladding completed.External plaster is in progress. 2nd storey i) 100% RCC slab & brick work completed.External plaster is in progress ii) 95% cement plaster completed. iii) 95% Unistone unibrick cladding completed. external plaster is in progress. 3rd storey i)Slab completed & 95% brick work completed. ii) 75% flooring completed.80% plaster work completed and balance work is in progress. iii) 95% unistone unibrick cladding completed. External plaster is in progress. 4th stroey. i)95% slab brick & Plaster work completed. ii) 75% flooring completed. iii) 95% Unistone unbrick cladding completed. External plaster is in progress. B) progress up to expansion joint. Complete in all respect.) 2nd storey-complete in allrespect.Final touching of point is in progress. iii)3rd storey-Complete in all respect .Final touching of paint is in progress. 4th storey Complete in all respect .Final touching of paint is in progress. iC) progress upto Next expansion joint. Ist Storey RCC slab ,brick work & Plaster completed.75% grid slab/ flooring completed. ii) 2nd storey-Slab completed.Brick work & plaster work completed.75% flooring completed. iii) 3rd stprey- Slab completed ,95% brick work & Plaster work completed & 75% flooring completed. IV 4th storey-95% slab ,brick work & plaster work completed.75% flooring completed,casting of column are in progress.
3 | BPSMV,Sonepat
a | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0.62 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.62 | 0 | 0.62 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and occupied by university authorities on 01.11.2014.
B.Sc labs for 93% work has been completed and the minor balance works like Paintaing,Electrical and Public Health works which are in progress and likely to be completed by 31.03.2015. The building was inspected on 01.10.2014 by the team consituted by Hon'ble VC i.e. DGM-III,HSRDC,Sonepat Architect,HOD of Department,who has to shift in the building . The hOD has desired some modification in the building and the archtect in the building and the architect has to submit the detail revised drawings, then the work will be taken in hand. The progress of work hampered due to non receipt of funds from university in time.
Research Scholar Hostel (Double story) :- 90% work has been completed and wooden joinery completed.Paintaing and electrical and public health works are in progress and likely to be completed by 31.03.2015.The progress of work hampered due to non receipt of funds from university in time.
Academic Staff Hostel 83% work has been completed. The balance works of flooring ,Palstering ,wooden Jonery ,Electrical and Public Healht works is in progress and likely to be completed by 31.03.2015. The progress of work hampered due to non receipt of funds fom university in time. Reaseach Scholar Hostel 80% wo
| Health Department | [19 empty] | Hostel for Degree college 83% work has been completed and wooden joinery completed.Paintaing and Electrical and Public Health works are in progress and likely to be completed by 31.03.2015. The progress of work hamperd due to non receipt of funds from university in time. Degree college Hostel 95% work has been completed. The balance work of Paintaing ,wooden Joinery ,Electrical & Public Health works are in progress and likely to be completed by 31.03.2015. The progress of work hampered due to non receipt ogf funds from university in time.
a | Construction of additional block at district Hospital Panipat | 43 | - | [9 empty] | 0 | 0 | [6 empty] | Work allotted democration of alignment of building ,removing of tress, electric poles ,sewer line is in progress
b | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.33 | 0.08 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 80% | Revised Admoinistrative approval of the work amounting of Rs. 5.00 crore has been acorded vide additional chief secretary to Govt.haryana Health Dept.vide no.20/59/2011-5HBIII dated 24.12.2014 whereas agreement of the work with the contractor is of Rs.549.42 lacs.S.E Rewari circle rewari circle rewari has already requested to ED HSRDC Panchkula vide letetr No.577 dated 30.01.2015 that permission may kindly be given to execute the work upto agreement amount as the revised estimate is under process and the same will be submitted shortly to get the revised .Administrative approval from the Health department.
c | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | #REF! | 0.98 | 8.98 | -7.43
131.901

## aug 2014
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.07.2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 |  | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | Work completed | 5.82 |  | 3.82
Work likely to be enhanced upto 6.15 crs
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | work completed | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 |  | 23.1315 | Agreement Terminated | 22.03 | 72.3% | work completed | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 |  | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | work completed
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 |  | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | work completed
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 |  | 4.24 |  | 4.04 | 100% | Work completed. Building hand over
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 |  | 2.1 |  | 2.28 | 98% | work completed .building hand over
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2.2995 | Completed except P.C. | 2.19 | 100% | Work completed | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 85% | work completed
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 |  | 9.408 | 2010-02-15 | 8.96 | 80% | 1.work completed building hand over. 2. Only officer club completed upto 40% and to be completed within two months. | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 |  | 3.6645 | 31 Jan.2010 | 3.04 | 100% | work completed | 1.07
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 |  | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | work completed | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | work completed | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 |  | 4.7775 | 31.01.2010 | 4.55 | 100% | work completed | 3.48
| TOTAL | 64.72 | #REF! | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 |  | 63.46 |  | 60.27
| Supervision Consultancy Charges | [15 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [15 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency. Now work completed.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work comp
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.01 | 0.03 | 0.04 | 1.09 | 1.09 | 5.12.2010 | 22.96 | 100% | Work completed in all respect on dated 20.12.2013 and CIPET building handed over to client department on dated 28.02.2014
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | Work completed
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
PGRC,Jind
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 16.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0 | 0 | 0 | 5.54 | 5.54 |  | 24.13 | 100% | Overall ProgressReport Mess Block- Completed in all respect. Hostel Block Completed in all respect except one finishing coat and fixed glass.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota s
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 | 1.24 |  | 16.10.2013 | 15.02.2014 31.03.2014(revised) | 0 | 0 | 0 | 0 | 0 | 0.44 | 44.04 | 0 | 0.95 |  | 0 |  | 0.95 |  | Work completed
BPSMV,Sonepat
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and ready for handing over to the BPSMV Khanpur kalan authority. The university authority hasrequested to EE,Electrical PWD B&R Br., Karnal for fixing 30 Nos,spilt AC before taking over the building.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- 93% work has been completed and the minor balances works like pinting ,electrical and Public health works which are in progres and likely to be completed by 15.11.2014. The progress of work hampered due to to non receipt of funds from university in time. The buiding was inspected on 01.10.2014 by the team consituted by Hona'ble VC i.e. under signed .Architct ,HOD of Department Who has to shift in the building .The HOD has desired some modification in the building and the architect is to submit to revised drawings, then the work will be taken in hand.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work 98% completed and balance work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- 90% work has been completed and the minor balance works like aluminium jonery , Painting ,Electrical and Public Health works are in progress and likely to be completed by 31.08.2014. Reaseach Scholar Hostel 85% work has been completd and the flooring in2nd storey and wooden joinery completed. painting and Electrical and Public Health works which are in progress and likely to be completed by 15.11.2014. The progress of work hampered due to non receipt of funds from university in time. Acadamic Staff Hostel : 70% work has been completed. The brick work on ground floor completed and balance brick work of 1st floor is in progress. The balance works of flooring ,wooden joinery ,Electrical and public and public health works willbe started soon and likely to be completed by 30.11.2014. The progress of work hampered due to non receipt of funds from university in time.
Hostel for Degree college (SINGLE STOREY):- 95% work has be3n completed. The balance work of paintaing , wooden joinery,Electrical & public health
Health Department
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Tender re-called and to be recived on 16.09.2014
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | ground floor 1st floor & 2nd floor slab work complete Third floor slab in progress, plaster work completed at G. floor & 1st floor & 2nd floor is in progress.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | 25.22 | 0.98 | 8.98 | -7.43
131.901

## ongoing works upto 31.07.2014
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.07.2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
1 | Construction of varius building at DCRTPP Colony Yamunanagar (Non residential) Agreement amount RS.542.81 lacs | 64.73 | 5.43 | 8.37 | 17.04.2008 | 16.02.2009/ 31.11.2013 | 0 | 0 | 0 | 1.42 | 1.56 | 0.75 | 0 | 0 | 0 |  | 3.72 |  | 9.30 overall 3.72 only in this office | 95% | 1.Works completed. Building hand over. 2.Only officer club completed upto 40% and to be completed within two months.
2 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work completed.
PGRC,Jind
a | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota stone
3 | BPSMV,Sonepat
a | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and ready for handing over to the BPSMV Khanpur kalan authority.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work 98% completed and balance work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- 90% work has been completed and the minor balance works like aluminium jonery , Painting ,Electrical and Public Health works are in progress and likely to be completed by 31.08.2014. Reaseach Scholar Hostel 80% wo
| Health Department | [19 empty] | Hostel for Degree college (SINGLE STOREY):- All slab, Brick work and plaster work completed,Joinery and flooring work is in progress..
a | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Tender re-called and to be recived on 16.09.2014
b | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | ground floor 1st floor & 2nd floor slab work complete Third floor slab in progress, plaster work completed at G. floor & 1st floor & 2nd floor is in progress.
c | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | #REF! | 0.98 | 8.98 | -7.43
131.901

## 31.07.2014
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.07.2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
1 | Construction of various houses of Group B-440 sft Block -5 770 sft & 1882 sft of Block 7& 12 houses at DCRTPP Yamunannagar (Balance work) agreement amount Rs.292.47 Lacs | RevisedA/A Rs.6472.98 Lacs vide DGM HSRDC Pkl No.710/HSRDC /NR dated 7.9.11 | 2.92 | 8.37 | 28.09.2011 | 27.06.2012/ 31.12.2012 | 0 | 0 | 0 | 0.69 | 1.57 | 0.16 | 0 | 0 | 0 |  | 2.42 |  | 2.42 | 100% | Work completed and building had over.
2 | Construction of varius building at DCRTPP Colony Yamunanagar (Non residential) Agreement amount RS.542.81 lacs |  | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.11.2013 | 0 | 0 | 0 | 1.42 | 1.56 | 0.75 | 0 | 0 | 0 |  | 3.72 |  | 9.30 overall 3.72 only in this office | 95% | 1.Works completed. Building hand over. 2.Only officer club completed upto 40% and to be completed within two months.
3 |  |  | 5.37 |  | 16.03.2012 | 15.03.2013 / 31.01.2014 | 0 | 0 | 0 | 0 | 1.51 | 3.8 | 0.59 | 0 | 0 |  | 5.9 |  | 6.17 | 100% | Work completed and building had over.
| GRAND TOTAL |  | 13.72 | 8.37 |  |  |  | 0 | 0 | 0 | 2.11 | 4.63 | 4.71 | 0.59 | 0 | 0 | 12.04 |  | 17.89/ 12.31
2 | Rajiv Gandhi Thermal Power Project, Khedar | [15 empty] | 24.08
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency. Now work completed.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work comp
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.01 | 0.03 | 0.04 | 1.09 | 1.09 | 5.12.2010 | 22.96 | 100% | Work completed in all respect on dated 20.12.2013 and CIPET building handed over to client department on dated 28.02.2014
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | work completed
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 16.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0 | 0 | 0 | 5.54 | 5.54 |  | 24.13 | 100% | Overall ProgressReport Mess Block- Completed in all respect. Hostel Block Completed in all respect except one finishing coat and fixed glass.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota stone
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 | 1.24 |  | 16.10.2013 | 15.02.2014 31.03.2014(revised) | 0 | 0 | 0 | 0 | 0 | 0.44 | 44.04 | 0 | 0.95 |  | 0 |  | 0.95 |  | Work completed
BPSMV,Sonepat
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and ready for handing over to the BPSMV Khanpur kalan authority.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work 98% completed and balance work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- 90% work has been completed and the minor balance works like aluminium jonery , Painting ,Electrical and Public Health works are in progress and likely to be completed by 31.08.2014. Reaseach Scholar Hostel 80% wo
Hostel for Degree college (SINGLE STOREY):- All slab, Brick work and plaster work completed,Joinery and flooring work is in progress..
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Tender re-called and to be recived on 16.09.2014
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | ground floor 1st floor & 2nd floor slab work complete Third floor slab in progress, plaster work completed at G. floor & 1st floor & 2nd floor is in progress.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% com | 25.22 | 0.98 | 8.98 | -7.43
131.901

## July 14
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.07.2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.07.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (July,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 |  | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | Work completed | 5.82 |  | 3.82
Work likely to be enhanced upto 6.15 crs
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | work completed | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 |  | 23.1315 | Agreement Terminated | 22.03 | 72.3% | work completed | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 |  | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | work completed
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 |  | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | work completed
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 |  | 4.24 |  | 4.04 | 100% | Work completed. Building hand over
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 |  | 2.1 |  | 2.28 | 98% | work completed .building hand over
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2.2995 | Completed except P.C. | 2.19 | 100% | Work completed | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 85% | work completed
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 |  | 9.408 | 2010-02-15 | 8.96 | 80% | 1.work completed building hand over. 2. Only officer club completed upto 40% and to be completed within two months. | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 |  | 3.6645 | 31 Jan.2010 | 3.04 | 100% | work completed | 1.07
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 |  | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | work completed | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | work completed | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 |  | 4.7775 | 31.01.2010 | 4.55 | 100% | work completed | 3.48
| TOTAL | 64.72 | #REF! | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 |  | 63.46 |  | 60.27
| Supervision Consultancy Charges | [15 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [15 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency. Now work completed.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 36.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 31.03.2015(revised ) | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 1.12 | 0 | 0.01 | 0.01 | 36.3 | 1.81 | 5.12.2010 | 38.11 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Conevention centre 1.G.F Brick work & Plaster work 95% completed. 2.1st floor brick work and plaster work 75% completed. 3. 2nd floor brick work and plaster work 60% completed. 4.Buffet area brick work and plaster work completed. 5.Dholpur stone work completed 95% . 6. Air-in take 1&2 completed and 3 Air in take 20%. 7.External PHE work 99% completed. 8. Stair case 3,7,4 & 6 cmpleted.upto mumty level.Machine room foors slab and roof alb completed. 9 Flooring of Kota stone in progress,shuttering work for slab at 12.215 Mtr. level is in progress. Physical progress in percentage of convention centre =60% Agency M/s Omaxe Ltd. terminated vide M.D HSRDC Memo no.9149/HSRDC/2013 dated 02.09.2013 The balance work allotted to M/s Gawar const Ltd.
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.01 | 0.03 | 0.04 | 1.09 | 1.09 | 5.12.2010 | 22.96 | 100% | Work completed in all respect on dated 20.12.2013 and CIPET building handed over to client department on dated 28.02.2014
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | Work completed
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
PGRC,Jind
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 16.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0 | 0 | 0 | 5.54 | 5.54 |  | 24.13 | 100% | Overall ProgressReport Mess Block- Completed in all respect. Hostel Block Completed in all respect except one finishing coat and fixed glass.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 06.01.2012 | 05.102013 30.12.2014Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0 | 0 | 0 | 6.78 | 4.72 |  | 4.5 | 65% | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota stone flooring completed. VI) Unistone unibrick cladding outer & internal plaster external & internal painting is in progress.
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 | 1.24 |  | 16.10.2013 | 15.02.2014 31.03.2014(revised) | 0 | 0 | 0 | 0 | 0 | 0.44 | 44.04 | 0 | 0.95 |  | 0 |  | 0.95 |  | Work completed
BPSMV,Sonepat
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 30.08.2012 310.09..2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 2.61 | 0.18 | 0.91 | 1.09 | 9.09 | 4.9 |  | 4.67 |  | Administrative Block The work completed in all respect and ready for handing over to the BPSMV Khanpur kalan authority.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work 98% completed and balance work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- 90% work has been completed and the minor balance works like aluminium jonery , Painting ,Electrical and Public Health works are in progress and likely to be completed by 31.08.2014. Reaseach Scholar Hostel 80% work has been completed and the minor balance works like Flooring ,wooden joinery,Painting Electrical and Public Health works are in progress and likely to be completed by 31.08.2014 Acadamic Staff Hostel 55% work has been completed.The shuttering of 2nd floor slab and brick work of ground floor is in progress. The slab will be laid upto 12.07.2014. The balance works of flooring wooden jonery ,electricaland Public Health works will be started soon and likely to be completed by 30.09.2014 Degree colllege Hostel 85% work has been completed. the balance work of Planning wooden joinery electrical & Public Health works are in progress and likely to be completed by 31.08.2014
Hostel for Degree college (SINGLE STOREY):- All slab, Brick work and plaster work completed,Joinery and flooring work is in progress..
Health Department
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Tender re-called and to be recived on 16.09.2014
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 0.09 | 0.14 | 0.23 | 3.49 upto 30.04.14 | 3.72 |  | 3.44 | 70% | ground floor 1st floor & 2nd floor slab work complete Third floor slab in progress, plaster work completed at G. floor & 1st floor & 2nd floor is in progress.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | Ground floor: Roof slab complete,Brick work completed plastering work completed,flooring completed,Joinery work 80% completed. First Floor: Roof slab complete , Brick work completed,Plastering work 95% completed,Flooring 80% completed,Joinery work 80% completed.Tile terracing completed. Initally work delayed on account of stay order by the Hon'ble cpourt Ch.Dadri and stay got vacated from the Hon'ble Court Distt.Judge Bhiwani. 2. Scope of work imcreased. 3. Shortage of budget. 4.Shortage of labour. | 25.22 | 0.98 | 8.98 | -7.43
131.901

## May 14
PHYSICAL & FINANCIAL PROGRESS REPORT (Upto 31.05.2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2014-2015 |  |  | Expenditure upto 31.05.14 | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (May,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 |  | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 |  | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | ( i )Barracks | 5.82 |  | 3.82
[21 empty] | ( ii ) Shops |  |  | 0.23
[21 empty] | ( iii ) Boundary wall |  |  | 0.9
[21 empty] | ( iii ) Dining Hall |  |  | 0.39
[21 empty] | ( iv ) Armoury |  |  | 0.44
( v ) Category-I
( vi ) Category-II
| Work likely to be enhanced upto 6.15 crs | [19 empty] | ( vii ) Type -III Category-III
( viii ) Type -IV Category-IV
Completed and occupied
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | Completed. Expenditure increases due to enhanced scope of work. | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 |  | 23.1315 | Agreement Terminated | 22.03 | 72.3% | Work done, Rs 20.81 crore, Secure Advance Rs 1.22 crore = Total - 22.03 crores (Tender Amount - Rs. 30.47 crores) | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 |  | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | 440 Sft Block-III: - Completed and handed over.
[13 empty] | 0 | [7 empty] | 440 Sft Block-IV: - -Brick work 97% , B/work of parapet 90% & mumty's 100% completed. Chowkhats 82% completed . Work of laying internal GI pipes is 95% completed. Fixing of MS railing is 60%. Front Compound wall Brick work and plaster 100 % completed. In
[18 empty] | 15 Jan.2010 |  |  | 440 Sft Block-VI : - Brick work 100%,R CC work , chowkhats 95% completed . Internal GI work & PVC conduits 80% done.Scred at 1st,2nd,3rd floor completed, stair case plaster in progress. Plaster of in side 80% completed. Plaster of outside front wall &
[18 empty] | 28 Feb.2010 |  |  | 440 Sft Block-VII : - Termination notice issued on 04.03.2011.
[18 empty] | 28 Feb.2010 |  |  | 660 Sft Block-II :- R CC 97%, Brick work 95% completed and complete on 3rd floor. Slab completed, chowkhats 80% & plaster inside 75% completed. B/work of rear compound wall completed and front side is completed.Screed for frooling is completed & Brick w
[18 empty] | 28 Feb.2010 |  |  | 1220 Sft Block-II: - R CC , Brick work , chowkhats completed . Ramp work in progress, ground floor flooring 50% Filling of Tibbba in front and rear court yard in progress .Plaster in side & outer side completed. PVC conduit and GI completed. Laying ko
[18 empty] | 2010-02-15 |  |  | 1220 Sft Block-III : -R CC 98%, Brick work 88 % completed . Internal GI work 30% completed. MS Boxes PVC conduits 80% completed. Chowkhats 30% completed. Staircase kotah stone 80% completed. Brick work of compound wall 100% completed on rear side. Bal
[18 empty] | 31 Jan.2010 |  |  | 2600 Sft Block-I to III: - Strcuture work completed and plastering and other works in progress. Termination notice issued on 04.03.2011.
[18 empty] | 2010-02-15 |  |  | 2600 Sft Block-IV to VI : - Inspected but not taken over
[18 empty] | 31 Nov.2009 |  |  | 2775 Sft :- Handed over
GROUP - II
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 |  | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | Building completed and handed over.
[18 empty] | 31 March.2010 |  |  | 440 Sft Block-II : - Building completed and handed over.
[18 empty] | 31 March.2010 |  |  | 440 Sft Block-V: - R CC work, Brick work, chowkhats and plaster work 95%. Rear Compound wall & Kotah stone on Staircase steps & Balcony railings completed. Balance work is in progress. Termination notice issued on 04.03.2011.
[18 empty] | 31 March.2010 |  |  | 660 Sft Block-I :-R CC , Brick work , Wall tiles, chowkhats, internal GI work, MS Boxes PVC conduits & Plaster completed. Compound wall, flooring, Nerolac Suraksha, OBD, enemal paint, tile terracing, floor tiles, CC ramp & MS gate completed. External G
[18 empty] | 31 March.2010 |  |  | 770 Sft Block-I :- R CC & Brick work 100% completed . Internal GI work 70% completed. MS Boxes PVC conduits of inner wall 95% completed. PS chowkhats 95%, kota stone completed. Plaster inside & outside 95% & 90%, compound wall 100% & Laying of terrazo
[18 empty] | 31 March.2010 |  |  | 1220 Sft Block-I : -Building completed and handed over.
[18 empty] | 31 March.2010 |  |  | 1882 Sft Block-I to 6 : - Work completed and handed over
[18 empty] | 31 March.2010 |  |  | 1882 Sft Block-7 to 12 :- Structure work 90% completed, plastering and finishing work in progress. Termination notice issued on 04.03.2011.
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 |  | 4.24 |  | 4.04 | 100% | Work completed
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 |  | 2.1 |  | 2.28 | 98% | Work completed excepted 2 nos houses of 1882 sft which are held up due to stay from the court .
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2.2995 | Completed except P.C. | 2.19 | 100% | Work completed | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 85% | 5 buildings out of 7 buildings stand completed. 1.Officer club - Shuttering work for the lying of first floor slab is in progress material stocked for slabs.The beam is to be dismantld, letter has written to agency for the same. Agency yet to start the work will be completed by 30.09.2014. 2.Community Centre - HPGCL decided not to execute the work.
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 |  | 9.408 | 2010-02-15 | 8.96 | 80% |  | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 |  | 3.6645 | 31 Jan.2010 | 3.04 | 100% | (i) Maintenance Office :- Completed and handed over. | 1.07
[18 empty] | 31 Jan.2010 |  |  | (ii) Dispensary : - Completed and handed over.
[18 empty] | 31 Jan.2010 |  |  | (iii) Shopping Complex : - Completed and handed over
[18 empty] | 31 Jan.2010 |  |  | (iv) Bank & Post office : - Completed and handed over.
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 |  | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | Work completed on 15 Feb 2009. Testing electromechanical equipment completed from 15 Feb 09 to 04 March 09. Partial load of CISF complex already imposed, since 08 Aug 09. No problems encountered so far. HPGCL may be pursued / requested to get the electric | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | Completed. Expenditure increases due to enhanced scope of work. | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 |  | 4.7775 | 31.01.2010 | 4.55 | 100% | Heavy HT / LT equipment installation and laying of UG cables complete. Work completed,. | 3.48
| TOTAL | 64.72 | 69.74 | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 |  | 63.46 |  | 60.27
| Supervision Consultancy Charges | [15 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [15 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 |  | 47.1 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 0 |  | 28.28 | 31.12.2009. | 26.93 |  | Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 0 |  | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.19 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 | 0.37 | 0 | 0 | 0 |  | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 0 |  | 2.5 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 |  | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0 | 0 |  | 4.8 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 | 0 | 0 | 0 | 0 |  | 4.16 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0.23 | 0.33 | 0 | 0.75 | 0.04 | 0 | 0 | 0 |  | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 | 0 | 0 | 0 | 0 |  | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.05 | 0 | 0 | 0 |  | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 | 1% of estimated cost put to bid |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.52 | 29.62 | 10.19 | 4.08 |  | 0 | 0 | 0 |  | 137 |  | 130.55
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 39.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 |  | 0.12 | 0.17 | 0.29 |  | 1.81 | 5.12.2010 | 38.08 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Convention Centre :- 1.G.F Brick work & Plaster Work 95% completed. 2. 1st floor brick work and Plaster work 75% completed. 3. 2nd Floor Brick work and plaster work 60% completed. 3rd floor 80% and T.F.60%. Pcc grund floor completed 95% 4. Buffet area bri
12 | CIPET, Sonepat
4 | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.47 | 0 | 0.47 |  | 20.35 | 5.12.2010 | 19.34 |  | Work is Completed. Financial completion is in progress.
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 |  | 19.05 |  | 18.14 | 100% | Cat-II 48 nos houses (double storey) Work completed. Handed over
Type III - 36 no houses (Double storey) Work completed. Handed over.
Type IV - 30 nos houses (Double Storey) Work completed and handed over.
Type V - 5 nos houses (single storey) Work completed. Handed over
Type VI - 3 nos houses (single storey) Work completed. Handed over
Type VII - 1 nos houses (single storey) Work completed. Handed over
Service Building (Four storey) Complted
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 |  | 0 |  | 0.84 |  | Work completed
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 |  | 0 |  | 0.14 |  | Work completed
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 |  | 0 |  | 0.19 |  | Work completed
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 |  | 0 |  | 0.18 |  | Work completed |  |  | 0.93 | -1.75
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 |  | 20.46 |  | 19.49
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 6 |  | 17.08.2011 | 17.08.2012 30.04.2014 (revised) | 0 | 0 | 0.01 | 0.83 | 3.52 | 1.78 | 0.24 | 0 | 0.24 | 5.54 | 5.817 |  | 5.54 | 100% | Work completed. Fincial completion is under process.
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 05.10.2011 | 05.10.2012 07.06.2014(Revised) | 0 | 0 | 0 | 0.1 | 3.18 | 2.81 | 0.46 | 0 | 0.46 | 6.45 | 4.72 |  | 4.5 |  | Overall progress report 1st storey i) All foundation and Plinth completed. Ii) 95% R.C.C. slab, 95% brick work of super structure completed and balance work is in progress, iii) 95% cement plaster completed. Iv) 65% Grid slab laid completed. V) 65% Kota stone flooring completed. vi) Unistone unbrick cladding, outer & internal plaster, external & internal painting is in progress. 2nd Storey i) 95% R.C.C.slab, 95% brick work & 65% flooring completed. ii) 65% cement plaster completed iii) Unistone unbrick cladding, outer & internal plaster, external & internal painting is in progress. 3rd storey i) 95% slab laid and 95% brick work completed ii) 65% KOTA FLOORING & 65% PLASTER completed and balance work is in progress. iii) unistone unibrick cladding, outer & internal plaster, external & internal painting and aluminium joinery work is in progress. 4th storey i) 95% slab laid and 80% brick work completed. ii) Unistone unibrick cladding, outer & internal plaster, external and internal painting and aluminum joinery work is in progress B) Progress Up to Expansion Joint Complete in all respect ii) 2nd storey :- All slab, brick work, plaster work, flooring and eluminium joinery work completed. final touching of paint is in progress. iii) 3rd storey :- Slab, brick work, kota stone, flooring and plaster work completed. Joinery work and other Unistone unbrick cledding and painting is in progress. 4th Storey: Slab, brick work, kota stone flooring and plaster work completed. Joinery work and outer Unistone unibrick cladding and painting is in progress.
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 |  |  | 16.10.2013 | 15.02.2014 | 0 | 0 | 0 | 0 | 0 |  | 44.04 | 0 | 44.04 |  | 0 |  | 44.04 |  | Earthwork, stone aggregate G-I,G-II & G-III completed except main gate portion.
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 31.08.2012 31.05.2014(revised) | 0 | 0 | 0 | 1.59 | 3.51 | 0 | 0 | 0 | 0 | 7.58 | 4.9 |  | 4.67 |  | Administrative Block (DOUBLE STOREY) :- Building work completed accept some electricals work like fans etc and cleaning of floor is in progress and likely to be completed soon. Pending work of internal road is in progress.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 98% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work 98% completed and balance work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- Footing work and filling of earth completed. Casting of columns for ground floor completed and 1st slab laid and columns for 2nd storey is in progress Brick work is in progress
Hostel for Degree college (SINGLE STOREY):- All slab, Brick work and plaster work completed,Joinery and flooring work is in progress..
10 | Construction of additional block at district Hospital Panipat | 20 | - | [17 empty] | Detailed estimate /DNIT under preparation.
11 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 31.08.2014 | - | - | - | - | 1.02 | 0 | 2.47 | 0 | 2.47 | 3.49 upto 30.04.14 | 3.49 |  | 3.44 |  | ground floor 1st floor & 2nd floor slab work complete Third floor slab in progress, plaster work completed at G. floor & 1st floor & 2nd floor is in progress.
12 | Construction of additional block at district Hospital Dadri in Bhiwani Distt. | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 30.06.2014 | - | - | - | - | 1.98 |  |  |  |  | 5.33 | 4.02 |  | 3.83 |  | RCC work in foundation 98% complete. Ist level slab 98% completed. Ist level brick work 95% completed. 2nd level slab 100% completed. 2nd level brick work 95% completed. further work in progress. Initally work delayed on account of stay order by the Hon'ble Court Ch. Dadri and stay got vacated from the Hon'ble Court Distt. Judge Bhiwani | 40.63 | 0.98 | 8.98 | -7.43
131.901

## march 14
PHYSICAL & FINANCIAL PROGRESS REPORT (Jan 2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expdt 01.04.13 to 31.03.14 (Rs. In crores) | Expenditure during the year 2013-2014 |  |  | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[13 empty] | Upto previous month | During the month (April,14) | Cumulative during 2014-15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  |  | 0 | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | ( i )Barracks | 5.82 |  | 3.82
[20 empty] | ( ii ) Shops |  |  | 0.23
[20 empty] | ( iii ) Boundary wall |  |  | 0.9
[20 empty] | ( iii ) Dining Hall |  |  | 0.39
[20 empty] | ( iv ) Armoury |  |  | 0.44
( v ) Category-I
( vi ) Category-II
| Work likely to be enhanced upto 6.15 crs | [18 empty] | ( vii ) Type -III Category-III
( viii ) Type -IV Category-IV
Completed and occupied
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 |  | 0 |  | 0 | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | Completed. Expenditure increases due to enhanced scope of work. | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 |  | 0 |  | 0 | 23.1315 | Agreement Terminated | 22.03 | 72.3% | Work done, Rs 20.81 crore, Secure Advance Rs 1.22 crore = Total - 22.03 crores (Tender Amount - Rs. 30.47 crores) | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 |  | 0 | 0.12 | 0.12 | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | 440 Sft Block-III: - Completed and handed over.
[13 empty] | 0 | [6 empty] | 440 Sft Block-IV: - -Brick work 97% , B/work of parapet 90% & mumty's 100% completed. Chowkhats 82% completed . Work of laying internal GI pipes is 95% completed. Fixing of MS railing is 60%. Front Compound wall Brick work and plaster 100 % completed. In
[17 empty] | 15 Jan.2010 |  |  | 440 Sft Block-VI : - Brick work 100%,R CC work , chowkhats 95% completed . Internal GI work & PVC conduits 80% done.Scred at 1st,2nd,3rd floor completed, stair case plaster in progress. Plaster of in side 80% completed. Plaster of outside front wall &
[17 empty] | 28 Feb.2010 |  |  | 440 Sft Block-VII : - Termination notice issued on 04.03.2011.
[17 empty] | 28 Feb.2010 |  |  | 660 Sft Block-II :- R CC 97%, Brick work 95% completed and complete on 3rd floor. Slab completed, chowkhats 80% & plaster inside 75% completed. B/work of rear compound wall completed and front side is completed.Screed for frooling is completed & Brick w
[17 empty] | 28 Feb.2010 |  |  | 1220 Sft Block-II: - R CC , Brick work , chowkhats completed . Ramp work in progress, ground floor flooring 50% Filling of Tibbba in front and rear court yard in progress .Plaster in side & outer side completed. PVC conduit and GI completed. Laying ko
[17 empty] | 2010-02-15 |  |  | 1220 Sft Block-III : -R CC 98%, Brick work 88 % completed . Internal GI work 30% completed. MS Boxes PVC conduits 80% completed. Chowkhats 30% completed. Staircase kotah stone 80% completed. Brick work of compound wall 100% completed on rear side. Bal
[17 empty] | 31 Jan.2010 |  |  | 2600 Sft Block-I to III: - Strcuture work completed and plastering and other works in progress. Termination notice issued on 04.03.2011.
[17 empty] | 2010-02-15 |  |  | 2600 Sft Block-IV to VI : - Inspected but not taken over
[17 empty] | 31 Nov.2009 |  |  | 2775 Sft :- Handed over
GROUP - II
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 |  | 0 |  | 0 | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | Building completed and handed over.
[17 empty] | 31 March.2010 |  |  | 440 Sft Block-II : - Building completed and handed over.
[17 empty] | 31 March.2010 |  |  | 440 Sft Block-V: - R CC work, Brick work, chowkhats and plaster work 95%. Rear Compound wall & Kotah stone on Staircase steps & Balcony railings completed. Balance work is in progress. Termination notice issued on 04.03.2011.
[17 empty] | 31 March.2010 |  |  | 660 Sft Block-I :-R CC , Brick work , Wall tiles, chowkhats, internal GI work, MS Boxes PVC conduits & Plaster completed. Compound wall, flooring, Nerolac Suraksha, OBD, enemal paint, tile terracing, floor tiles, CC ramp & MS gate completed. External G
[17 empty] | 31 March.2010 |  |  | 770 Sft Block-I :- R CC & Brick work 100% completed . Internal GI work 70% completed. MS Boxes PVC conduits of inner wall 95% completed. PS chowkhats 95%, kota stone completed. Plaster inside & outside 95% & 90%, compound wall 100% & Laying of terrazo
[17 empty] | 31 March.2010 |  |  | 1220 Sft Block-I : -Building completed and handed over.
[17 empty] | 31 March.2010 |  |  | 1882 Sft Block-I to 6 : - Work completed and handed over
[17 empty] | 31 March.2010 |  |  | 1882 Sft Block-7 to 12 :- Structure work 90% completed, plastering and finishing work in progress. Termination notice issued on 04.03.2011.
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 |  | 1.79 | 0.74 | 2.53 | 4.24 |  | 4.04 | 90% | 1.440 sft houses blockno.4- Approx cost 200 Lac,Completed and ready for handing over. 2.1220 sft (Type-V) Block 2- Completed and ready to handed over Handed over 3.1220 sft (Type V) Bl 600 sft will be completed on or before 28.02.2014. Window panes,final
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 |  | 0.12 | 0 | 0.12 | 2.1 |  | 2.28 | 95%
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 |  | 0 |  | 0 | 2.2995 | Completed except P.C. | 2.19 | 70% |  | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 |  | 0 |  | 0 | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [18 empty] | 1. Transit Building - Ready for handing over.(Inspection by HPGCL) officers yet to be carried out. 2.Officer club - Shuttering work for the lying of first floor slab is in progress material stocked for slabs.(Work in progress)
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 |  | 0.34 | 0 | 0.34 | 9.408 | 2010-02-15 | 8.96 | 80% |  | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 |  | 0 |  | 0 | 3.6645 | 31 Jan.2010 | 3.04 | 100% | (i) Maintenance Office :- Completed and handed over. | 1.07
[17 empty] | 31 Jan.2010 |  |  | (ii) Dispensary : - Completed and handed over.
[17 empty] | 31 Jan.2010 |  |  | (iii) Shopping Complex : - Completed and handed over
[17 empty] | 31 Jan.2010 |  |  | (iv) Bank & Post office : - Completed and handed over.
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 |  | 0 |  | 0 | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | Work completed on 15 Feb 2009. Testing electromechanical equipment completed from 15 Feb 09 to 04 March 09. Partial load of CISF complex already imposed, since 08 Aug 09. No problems encountered so far. HPGCL may be pursued / requested to get the electric | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 |  | 0 |  | 0 | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | Completed. Expenditure increases due to enhanced scope of work. | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 |  | 0 |  | 0 | 4.7775 | 31.01.2010 | 4.55 | 100% | Heavy HT / LT equipment installation and laying of UG cables complete. Work completed,. | 3.48
| TOTAL | 64.72 | 69.74 | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 |  | 0 | 0.86 | 3.11 | 63.46 |  | 60.27
| Supervision Consultancy Charges | [14 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [14 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0.76 | 0 | 0 | 0 | 46.305 | 31.03.2010 | 44.1 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 |  | 0 | 0 | 0 | 28.28 | 31.12.2009. | 26.93 |  | Barracks of CISF - Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 |  | 0 | 0 | 0 | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0 |  | 0 | 0 | 0 | 2.42 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0.51 |  | 0.37 | 0 | 0.37 | 0.92 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 |  | 0 | 0 | 0 | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 |  | 0 | 0 | 0 | 2.3205 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 |  | 0 | 0 | 0 | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 |  | 0.16 | 0 | 0.16 | 4.809 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.83 |  | 0 | 0 | 0 | 4.14 | 28.02.2010. | 3.96 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0 | 0.33 | 0 | 0.75 |  | 0.04 | 0 | 0.04 | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0.01 |  | 0 | 0 | 0 | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 |  | 0.04 | 0.01 | 0.05 | 0.06 |  | 0.06
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0.66 |  |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 |  | 0 | 0 | 0 | 0.61 |  | 0.58 |  | Work in progress
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.29 | 29.62 | 10.19 | 4.08 |  | 0.61 | 0.01 | 0.62 | 135.628 |  | 129.79
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 39.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 |  | 0.12 | 0.17 | 0.29 | 1.81 | 5.12.2010 | 38.08 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Convention Centre :- 1.G.F Brick work & Plaster Work 95% completed. 2. 1st floor brick work and Plaster work 75% completed. 3. 2nd Floor Brick work and plaster work 60% completed. 3rd floor 80% and T.F.60%. Pcc grund floor completed 95% 4. Buffet area brick work and plaster work completed. 5. Dhoiplur stone work completed 95%. 6. Air-in-take 1& 2 completed and 3 Air in take 20% 7. Exteernal PHE work 99% completed. 8. Stair case 3, 7, 4 & 6 completed upto mumty level. Machine Room floors slab and roof slab completed Physical progress in percentage = 89%. Agency M/s Omaxe stopped work on 20.06.2013 and agency terminated vide MD HSRDC Memo no. 9149/HSRDC/2013 dated 02.09.2013. THe tender for balance work has been received which is under process.
4 | CIPET, Sonepat
a | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 |  | 0.47 | 0 | 0.47 | 20.35 | 5.12.2010 | 19.34 | 97% | Boundary Wall Completed. | 40.63 | 0.98 | 8.98 | -7.43
Guest House - Two storey 1RCC frame work and slab has been completed & flooring work is complted except toilets and main entrance area and building likely to be completed upto 31.11.2013. House Type-I Two Stroey Work is completed and handed over to CIPET
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 |  | 0 | 0 | 0 | 19.05 |  | 18.14 |  | Cat-II 48 nos houses (double storey) Work completed. Handed over
Type III - 36 no houses (Double storey) Work completed. Handed over.
Type IV - 30 nos houses (Double Storey) Work completed and handed over.
Type V - 5 nos houses (single storey) Work completed. Handed over
Type VI - 3 nos houses (single storey) Work completed. Handed over
Type VII - 1 nos houses (single storey) Work completed. Handed over
Service Building (Four storey) 1The work of service building stands completed.The fixture of Fire fighting work is yet to be fixed that will be fixed at the time of handing over the building.Civil work / PH work and E.I work completed.
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 |  | 0 | 0 | 0 | 0 |  | 0.84 |  | Both panel i.e motorized/ A.C panel has been enerized by the HPGCL.The Testing work is completed.
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 |  | 0 | 0 | 0 | 0 |  | 0.14 |  | Testing work is in progress.
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 |  | 0 | 0 | 0 | 0 |  | 0.19 |  | Electric Panel has been energized by the HPGCL on 25.09.2013
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 |  | 0 | 0 | 0 | 0 |  | 0.18 |  | Electric Panel has been energized by the HPGCL on 25.09.2013.Testing of tube fittings/Fans has almost completed.
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 |  | 0 | 0 | 0 | 20.46 |  | 19.49
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 4.8 |  | 17.08.2011 | 17.08.2012 | 0 | 0 | 0.01 | 0.83 | 2.62 |  | 0 | 0 | 0 | 4.37 |  | 4.16 |  | (A) Overallprogress Report Mess Block- Complete in all respect. i) Completed exceipt outer acllaric paint. Hostel Block Ist Storey Slab brick work plaster work, flooring work completed,finishing work, fixing of rading in staircase, fixing of sanitary intalations and fitting cupboard shutter in upper portion, wire gauge shutter, rubbing of flooring & fixing of glass in progress 2nd story slab, brick work, plasterwork, flooringwork completed. finishing work, fixing of railing in staricase, fixing of sanitary instalations and fitting, cupboard shutter in upper portion, wire gauge shutter rubbing of flooring & fixing of glass in progress. 3rd story slab, brick work, plasterwork, flooringwork completed, finishing work, fixing of railing in staircase, fixing of sanitary intalations and fitting cupboard shutter in upper portion, wire gauge shutter, rubbing offlooring & fixing of glass in progress 4th story slab brick work, plaster work flooring work completed. finishing work fixing of railing in staricase, fixing of sanitary intalation and fitting, cupboard shutter in upper portion, wire gauge shutter rubbing of flooring & fixing of glass in progress. |  |  | 0.93 | -1.75
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 05.10.2011 | 05.10.2012 | 0 | 0 | 0 | 0.1 | 3.08 |  | 0.42 | 0.26 | 2.81 | 4.72 |  | 4.5 |  | Overall Progtess Report Ist Storey Over all) 1. Foundaton and plinth completed and balance work is in progress. 2. 95% R.C.C Slab,95% brick work of Super Structure completed and balance work is in progress. 3. Brick work in foundation & plinth completed 4. 65% cement plaster completed. 5. 65% Grid slab laid completed 6. 65% Kota stone flooring completed 2nd story 1.) 95% R.C.C. slab, 95% brick work & 65% kota flooring completed. 2.) 65% Kota stone Flooring laid 3rd story 1.) 95% slab laid and 95% brick work completed 2.) 65% Kota Flooring & 65% plaster completed and balance work is in progress. 4th story 65% slab laid and 65% brick work completed. Laying of steel is in progress of balance slab B) Progress upto Expension joint complete in all respect. ii) 2nd story :- All slab including staircase completed, 70% inner plaster work, brick work, Kota flooring & joinery work completed, Sanitary fiting and outer and inner finishing work is in progress. iii) 3rd story :- slab laid & brick work completed 65% plaster work & kotah floor completed 4th Story Slab and brick work completed. Plaster and flooring work is in progress
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 |  |  | 16.10.2013 | 15.02.2014 | 0 | 0 | 0 | 0 | 0 |  | 44.04 | 0 | 44.04 | 0 |  | 44.04 |  | Earthwork, stone aggregate G-I,G-II & G-III completed except main gate portion.
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 31.08.2012 | 0 | 0 | 0 | 1.59 | 3.51 |  | 0.26 | 1.57 | 1.83 | 4.9 |  | 4.67 |  | Administrative Block (DOUBLE STOREY) :- All slab laid 100% vitrified tile flooring, 98% aluminium joinery, 90% wall putty, 100% false ceiling, 90% wooden flooring completed and balance work S.S. railing, sanitary work and electical work is in progress. (Likely to be completed upto 15.04.2014) pending work of internal road is in progress.
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- Slab, brick work and plaster work is completed. 80% vitrified tile flooring completed and balance work of aluminum joinery is in progress.
Research Scholar Hostel (Double story) :- 1st & 2nd storey slab laid, brick work completed and plaster work is in progress.
Academic Staff Hostel (DOUBLE STOREY) :- Footing work and filling of earth completed. Casting of columns for ground floor completed and 1st slab laid and columns for 2nd storey is in progress is in progress.Casting of coloumns for ground floor is in progress.
Hostel for Degree college (SINGLE STOREY):- All slab, Brick work and plaster work completed,Joinery and flooring work is in progress..
9 | Construction of additional block at district Hospital Panipat | 20 | - | [16 empty] | Detailed estimate /DNIT under preparation.
10 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 | - | - | - | - | 1.02 |  | 2.47 | 0 | 2.47 | 3.49 |  | 3.44 |  | ground floor 1st floor & 2nd floor slab work complete & plaster work, G.G. floor completed & 1st & 2nd floor in progress. 3rd floor slab in progress
11 | Construction of additional block at district Hospital Dadri | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 | - | - | - | - | 1.98 |  | 1.25 | 0.6 | 1.85 | 4.02 |  | 3.83 |  | RCC work in foundation 98% complete. Ist level slab 98% completed. Ist level brick work 90% completed. 2nd level slab 85% completed. 2nd level brick work 85% completed. further work in progress. Initally work delayed on account of stay order by the Hon'ble Court Ch. Dadri and stay got vacated from the Hon'ble Court Distt. Judge Bhiwani.
131.901

## jan 14
PHYSICAL & FINANCIAL PROGRESS REPORT (Jan 2014)
Sr No | Name of Work | Amount of A/A (Rs in crores) | Tender amount (Rs in Crores) | Funds Received (Rs in Crores) | Date of start | Stipulated Date of Completion / Target date of Completion | Expdt upto 31.03.09 (Rs. in crores) | Expdt 01.04.09 to 31.03.10 (Rs. In crores) | Expdt 01.04.10 to 31.03.11(Rs. In crores) | Expdt 01.04.11 to 31.03.12 (Rs. In crores) | Expdt 01.04.12 to 31.03.13 (Rs. In crores) | Expenditure during the year 2013-2014 |  |  | Uptodate cumulative Expenditure (in crores) including 5% HSRDC charges | Stipulated Date of Completion/Target date of Completion | Expenditure as per Agreement | Commulative upto date physical progress | Physical Progress/Remarks | Expenditure upto 28.2.2009 (Rs in crores)
[12 empty] | Upto previous month | During the month (Dec,2013) | Cumulative during 2013-14
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 11 | 17 | 18 | 19
1 | Deenbandhu Chottu Ram Thermal Power Project
a | Construction of CISF at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar, 347-B2, Shiv Colony, Pinor District, Panchkula) | 4.3972 | 3.82 | 62 | 22.11.2007 | work stands completed | 4.52 | 1.59 | 0 | 0 | 0 |  |  | 0 | 6.4155 | work stands completed | 6.11 | Work Stands completed on 15.02.2009 | ( i )Barracks | 5.82 |  | 3.82
[19 empty] | ( ii ) Shops |  |  | 0.23
[19 empty] | ( iii ) Boundary wall |  |  | 0.9
[19 empty] | ( iii ) Dining Hall |  |  | 0.39
[19 empty] | ( iv ) Armoury |  |  | 0.44
( v ) Category-I
( vi ) Category-II
| Work likely to be enhanced upto 6.15 crs | [17 empty] | ( vii ) Type -III Category-III
( viii ) Type -IV Category-IV
Completed and occupied
b | Construction of OHSR at Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Narayan Goyal) |  | 0.23 |  | 28.11.2007 | work stands completed | 0.2 | 0.02 | 0 | 0 | 0 | 0 |  | 0 | 0.231 | work stands completed | 0.22 | Work Stands completed on 30.04.2008 | Completed. Expenditure increases due to enhanced scope of work. | 0.29
c | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (M/s Starrco Engineers) | 26.6783 | 30.47 |  | 19.09.2007 | Agreement Terminated on 24.08.09 | 19.48 | 2.55 | 0 | 0 | 0 | 0 |  | 0 | 23.1315 | Agreement Terminated | 22.03 | 72.3% | Work done, Rs 20.81 crore, Secure Advance Rs 1.22 crore = Total - 22.03 crores (Tender Amount - Rs. 30.47 crores) | 20.86
c (1) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group-I) (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.85 |  | 05.10.09 | 30/04/2010 Termination notices issued on 04.03.2011 | 0 | 0.94 | 1.28 | 0 | 0 | 0 | 0.12 | 0.12 | 2.457 | 15 Feb 2010. | 2.34 | 36.7% | 440 Sft Block-III: - Completed and handed over.
[12 empty] | 0 | [6 empty] | 440 Sft Block-IV: - -Brick work 97% , B/work of parapet 90% & mumty's 100% completed. Chowkhats 82% completed . Work of laying internal GI pipes is 95% completed. Fixing of MS railing is 60%. Front Compound wall Brick work and plaster 100 % completed. In
[16 empty] | 15 Jan.2010 |  |  | 440 Sft Block-VI : - Brick work 100%,R CC work , chowkhats 95% completed . Internal GI work & PVC conduits 80% done.Scred at 1st,2nd,3rd floor completed, stair case plaster in progress. Plaster of in side 80% completed. Plaster of outside front wall &
[16 empty] | 28 Feb.2010 |  |  | 440 Sft Block-VII : - Termination notice issued on 04.03.2011.
[16 empty] | 28 Feb.2010 |  |  | 660 Sft Block-II :- R CC 97%, Brick work 95% completed and complete on 3rd floor. Slab completed, chowkhats 80% & plaster inside 75% completed. B/work of rear compound wall completed and front side is completed.Screed for frooling is completed & Brick w
[16 empty] | 28 Feb.2010 |  |  | 1220 Sft Block-II: - R CC , Brick work , chowkhats completed . Ramp work in progress, ground floor flooring 50% Filling of Tibbba in front and rear court yard in progress .Plaster in side & outer side completed. PVC conduit and GI completed. Laying ko
[16 empty] | 2010-02-15 |  |  | 1220 Sft Block-III : -R CC 98%, Brick work 88 % completed . Internal GI work 30% completed. MS Boxes PVC conduits 80% completed. Chowkhats 30% completed. Staircase kotah stone 80% completed. Brick work of compound wall 100% completed on rear side. Bal
[16 empty] | 31 Jan.2010 |  |  | 2600 Sft Block-I to III: - Strcuture work completed and plastering and other works in progress. Termination notice issued on 04.03.2011.
[16 empty] | 2010-02-15 |  |  | 2600 Sft Block-IV to VI : - Inspected but not taken over
[16 empty] | 31 Nov.2009 |  |  | 2775 Sft :- Handed over
GROUP - II
c (ii) | Construction of houses at Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar (Balance work Group- II). (M/s Savvy Construction Pvt. Ltd,) Work likely to be enhanced upto 6.00 crs |  | 4.42 |  | 05.10.09 | 31.03.2010 Termination notices issued on 04.03.2011 | 0 | 1.55 | 0.59 | 0 | 0 | 0 |  | 0 | 2.247 | 15 Jan.2010 | 2.14 | 48.41% | Building completed and handed over.
[16 empty] | 31 March.2010 |  |  | 440 Sft Block-II : - Building completed and handed over.
[16 empty] | 31 March.2010 |  |  | 440 Sft Block-V: - R CC work, Brick work, chowkhats and plaster work 95%. Rear Compound wall & Kotah stone on Staircase steps & Balcony railings completed. Balance work is in progress. Termination notice issued on 04.03.2011.
[16 empty] | 31 March.2010 |  |  | 660 Sft Block-I :-R CC , Brick work , Wall tiles, chowkhats, internal GI work, MS Boxes PVC conduits & Plaster completed. Compound wall, flooring, Nerolac Suraksha, OBD, enemal paint, tile terracing, floor tiles, CC ramp & MS gate completed. External G
[16 empty] | 31 March.2010 |  |  | 770 Sft Block-I :- R CC & Brick work 100% completed . Internal GI work 70% completed. MS Boxes PVC conduits of inner wall 95% completed. PS chowkhats 95%, kota stone completed. Plaster inside & outside 95% & 90%, compound wall 100% & Laying of terrazo
[16 empty] | 31 March.2010 |  |  | 1220 Sft Block-I : -Building completed and handed over.
[16 empty] | 31 March.2010 |  |  | 1882 Sft Block-I to 6 : - Work completed and handed over
[16 empty] | 31 March.2010 |  |  | 1882 Sft Block-7 to 12 :- Structure work 90% completed, plastering and finishing work in progress. Termination notice issued on 04.03.2011.
C (A) | Balance work for constructiono f residetial houses of Group A 440 sft, Block 4&6, 660 sft block 2, 1220 sft block no. 2 and 3, 2600 sft block no. 1 to 6 and 2775 sft house block at DCRTPP Y. Nagar | 3.85 | 5.37 |  | 16.03.12 | 15.03.2013/ 31.01.2014 | 0 | 0 | 0 | 0.4 | 1.51 | 1.79 | 0.74 | 2.53 | 4.24 |  | 4.04 | 90% | 1.440 sft houses blockno.4- Approx cost 200 Lac,Completed and ready for handing over. 2.1220 sft (Type-V) Block 2- Completed and ready to handed over Handed over 3.1220 sft (Type V) Bl 600 sft will be completed on or before 28.02.2014. Window panes,final grinding ,final paint ,electrical fixture,Public Health Fixture is pending.
C (B) | Construction of various houses of Group B, 440 sft block 5, 770 sft and 1882 sft block 7-12 block houses (balance work) at DCRTPP Y. Nagar. | 2.25 | 2.92 |  | 28.09.2011 | 27.06.2012/ 31.12.2013 | 0 | 0 | 0 | 0.4 | 1.58 | 0.12 | 0 | 0.12 | 2.1 |  | 2.28 | 95%
d | Construction of internal roads in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Jai Bhagwan Contractor) Work likely to be reduced upto 3.30 cr | 4.2986 | 4.3 |  | 14.01.2008 |  | 1.53 | 0.66 | 0 | 0 | 0 | 0 |  | 0 | 2.2995 | Completed except P.C. | 2.19 | 70% |  | 1.61
e | Providing Water Supply, Sewerage & Water Drainage System in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar (Vijay Kumar Contractor) Work likely to be enhanced upto 1.19 crs. |  | 0.9 |  | 01.02.2008 |  | 1.08 | 0.11 | 0 | 0 | 0 | 0 |  | 0 | 1.2495 | Completed | 1.19 | Work stands completed on 20.02.2009 | Work completed. | 1.13
f | Construction of Non Residential Buildings in Deenbandhu Chhottu Ram Thermal Power Project at Yamuna Nagar | [17 empty] | 1. Transit Building - Ready for handing over.(Inspection by HPGCL) officers yet to be carried out. 2.Officer club - Shuttering work for the lying of first floor slab is in progress material stocked for slabs.(Work in progress)
| 1. Various Buildings (7 nos) (M/s Tech Spere) | 9.8096 | 5.43 |  | 17.04.2008 | 16.02.2009/ 31.12.2013 | 0 | 0 | 5.65 | 1.42 | 1.55 | 0.34 | 0 | 0.34 | 9.408 | 2010-02-15 | 8.96 | 80% |  | 1.9
2010-02-15
15 Jan.2010
28 Feb.2010
28 Feb.2010
31 March.2010
31 Jan.2010
| 2. Shopping complex, Dispensary, Bank, Post Office and Maintenance Office (4 nos) (M/s Tech Spere) Work likely to be enhanced upto Rs.2.30 crores. |  | 2 |  | 15.05.08 | 14/01/2009 15/04/2011 | 0.27 | 1.59 | 1.18 | 0.45 | 0 | 0 |  | 0 | 3.6645 | 31 Jan.2010 | 3.04 | 100% | (i) Maintenance Office :- Completed and handed over. | 1.07
[16 empty] | 31 Jan.2010 |  |  | (ii) Dispensary : - Completed and handed over.
[16 empty] | 31 Jan.2010 |  |  | (iii) Shopping Complex : - Completed and handed over
[16 empty] | 31 Jan.2010 |  |  | (iv) Bank & Post office : - Completed and handed over.
g | Construction of Sewerage Treatment plant in the colony of Deenbandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (M/s Hydrotech Paryawaran Pvt. Ltd, Phase VII, Mohali) |  | 0.39 |  | 05.08.08 | 24/08/2008 15/02/2009 | 0.28 | 0.06 | 0.01 | 0 | 0 | 0 |  | 0 | 0.3675 | Completed | 0.35 | Work Stands completed on 15.02.2009 | Work completed on 15 Feb 2009. Testing electromechanical equipment completed from 15 Feb 09 to 04 March 09. Partial load of CISF complex already imposed, since 08 Aug 09. No problems encountered so far. HPGCL may be pursued / requested to get the electric | 0.3
h | Construction of Electrical sub station at Deen Bandhu Chhotu Ram Thermal Power Project at Yamuna Nagar. (Vijay Kumar Contractor) Work likely to be enhanced upto 0.83 crs | 4.2499 | 0.44 |  | 14.11.08 | 13/02/2009 31/03/2009 | 0.32 | 0.51 | 0 | 0 | 0 | 0 |  | 0 | 0.8715 | (i) Sub station -I : - completed. | 0.83 | Work Stands completed on 31.03.2009 | Completed. Expenditure increases due to enhanced scope of work. | 0.79
i | Prov of 11 KV sub station including Electric Supply to buildings and street lights in DCRTPP colony (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hisar) Work likely to be enhanced upto 4.70 crs |  | 4.2 |  | 26.09.08 | 25/03/2009 31/03/2010 | 1.28 | 3.05 | 0.22 | 0 | 0 | 0 |  | 0 | 4.7775 | 31.01.2010 | 4.55 | 100% | Heavy HT / LT equipment installation and laying of UG cables complete. Work completed,. | 3.48
| TOTAL | 64.72 | 69.74 | 62 |  |  | 28.96 |  | 8.93 | 2.67 | 4.64 | 0 | 0.86 | 3.11 | 63.46 |  | 60.27
| Supervision Consultancy Charges | [13 empty] | 1.428 |  | 1.36
| GRAND TOTAL | [13 empty] | 64.888 |  | 61.63
2 | Rajiv Gandhi Thermal Power Project, Khedar
a | Construction of 144 Nos. Type V and 24 Nos. Type VI Houses in the campus of RGTPP at Khedar in Hisar Distt. (Telecommunication Consultant India Ltd, TCIL Bhawan Greater Kailash-I, New Delhi) | 32.29 | 32.29 |  | 12.09.08 | 11/03/2010 30/11/2011 | 8.39 | 20.68 | 11.71 | 3.32 | 0 | 0 | 0.76 | 0.76 | 47.103 | 31.03.2010 | 44.86 |  | Work Completed
b | Construction of CISF campus and non residential buildings in the campus of RGTPP at Khedar in Hisar Distt. (M/s Goel Co. Pvt. Ltd, 230 City Centre, SC Road Jaipur) | 15.9 | 15.9 |  | 01.10.08 | 31/12/2009 30/09/2011 | 5.83 | 13.93 | 4.73 | 0.64 | 1.8 | 0 | 0 | 0 | 28.28 | 31.12.2009. | 26.93 |  | Barracks of CISF - Work completed
c | Construction of 48 nos. type - II, 96 nos. type - III, 96 nos type - IV (G+ 3 storey ) 8 nos type -VII (Duplex) and 1 no type VIII (Duplex) Houses in the campus of RGTPP at Khedar in Hisar Distt. (City promoters & Buildwell Pvt. Ltd, P-18, Ansal Complex, | 22.79 | 22.79 |  | 20.11.08 | 19/07/2010 15.03.2012 | 5.27 | 20.51 | 10.1 | 5.48 | 0 | 0 | 0 | 0 | 43.428 | 19.07.2010. | 41.36 |  | Work completed.
d (1) | Constn of Internal Roads in the campus of RGTPP at Khedar in Hissar Distt. (M/s Hissar Friend Colony Coop. L&C Society Ltd, 74-E, Gali No. 11, Jawaher Naser, Delhi) | 2.52 | 2.52 |  | 11.11.08 | 10/5/2009 31.03.2012 | 0 | 1.76 | 0.33 | 0 | 0.21 | 0 | 0 | 0 | 2.42 | 31.12.2009. | 2.09 |  | Work terminated and the balance work allotted to another agency.
d (2) | Construction of internal roads in the campus of RGTPP, Khedar Hisar (M/s Balaji Construction Company) |  | 1.05 |  | 3.4.2012 | 2.7.12 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.51 | 0.88 | 0.924 | 31.12.2009. | 0.88 |  | Work completed.
e | Constn of OHSR of 3.0 Lacs Litrs. Capacity in the campus of RGTPP at Khedar in Hissar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 0.3 | 0.3 |  | 10.02.09 | 9/6/2009 2/7/2009 | 0 | 0.27 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0.3045 | Work completed on 02.07.2009. | 0.29 |  | Work Completed
f | Construction of strom water drain and water supply system in the campus of RGTPP at Khedar in Hisar Distt. (Waterman Engg. 40-S Model Town, Hissar) | 2.35 | 2.35 |  | 10.02.09 | 9/8/2009 31/10/2011 | 0 | 2 | 0.2 | 0.01 | 0.17 | 0 | 0 | 0 | 2.3205 | 31.12.2009. | 2.38 |  | Work completed
g | Construction of Sewerage treatment plan in the campus of RGTPP at Khedar in Hissar Distt. (M/s Eco Paryawaran Engg. & Consultant Pvt. Ltd, 1225/1, Sector 34-C, Chandigarh) | 0.42 | 0.42 |  | 22.10.08 | 21/02/2009 30/09/2009 | 0 | 0.43 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0.4725 | Work completed on 30.09.2009. | 0.45 |  | Work completed
h | Construction of Boundry wall (Retaining wall type) around the toun ship of RGTPP at Khedar in Hissar Distt. (M/s Goel Construction Co. Pvt. Ltd, 230, City Centre, SC Road, Jaipur) | 4.84 | 4.84 |  | 09.03.09 | 08/01/2010 31/01/2010 | 0 | 4.21 | 0 | 0.21 | 0 | 0.16 | 0 | 0.16 | 4.809 | 08.01.2010. | 4.58 |  | Work Completed
i | Providing 11 Kv elcetrical sub station & connectin to various houses/ buildings and providing street lighting on roads in the campus of RGTPP at Khedar. (M/s Ishwar Singh & Associates, 107, Azad Nagar, Hissar) | 3.45 | 3.45 |  | 01.06.09 | 30/11/2009 31/10/2011 | 0 | 1.15 | 1.73 | 0.25 | 0.81 | 0 | 0 | 0 | 4.14 | 28.02.2010. | 3.94 |  | Work completed
j | Supply, Installation testing & commencering of 8 no elevator of 8 passengers in Type V- VII houses. | Not received | 1.29 |  | 21/08/09 | 20/02/2010 30.04.2012 | 0 | 0 | 0.32 | 0 | 0.99 | 0.04 | 0 | 0.04 | 1.42 |  | 1.35 |  | Work completed
j | Providing Electrical fixtures in residential and non residential buildings at RGTPP Khedar in Hissar district. | 0.99 |  |  |  | 31.03.2012 | 0 | 0.15 | 0.36 | 0.26 | 0 | 0 | 0 | 0 | 0.8085 |  | 0.78 |  | Work completed.
k | Expenditure by other mode i.e through HR & work order | [5 empty] | 0 | 0 | 0 | 0 | 0.01 | 0.02 | 0 | 0.02 | 0.03 |  | 0.03
l | Engagement of Architect consultant for construction of colony RGTPP at khedar | 0 |  |  | 27.05.2008 | 13.09.2008 | 0.22 | 0.2 | 0.11 | 0.05 | 0 | 0 | 0 | 0 | 0.61 |  | 0.58
| TOTAL | 84.86 | 87.2 | 132.9 |  |  | 19.71 | 65.29 | 29.61 | 10.19 | 3.99 | 0.59 | 1.27 | 1.86 | 136.43 |  | 130.5
3 | Convention Centre Sonepat
a | Construction of Convention Centre, Library and Computer Centre at Deenbandhu Chhottu Ram University of Science and Technology at Murthal in Sonipat Distt. (M/s Omaxe) | 56.4 | 39.96 | 36.45 | 06.06.2009 | For Library building 30.9.12 For Convention centre 31.12.12 | 0.38 | 11.68 | 9.06 | 6.29 | 7.76 | 0.42 | 0.43 | 0.85 | 39.71 | 5.12.2010 | 37.82 | 89% | Library Block Library block completed.Inaugrated by Hon'ble C.M Haryana on dated 13.06.2013 |  | -2.11 | 7.21 | -6.28
Convention Centre :- 1.G.F Brick work & Plaster Work 95% completed. 2. 1st floor brick work and Plaster work 75% completed. 3. 2nd Floor Brick work and plaster work 60% completed. 4. Buffet area brick work and plaster work completed. 5. Dhoiplur stone wor
4 | CIPET, Sonepat
a | Construction of building for CIPET project at DCRUST Murthal in Sonepat District. | 24.95 | 14.88 | 24.95 | 16.04.2010 | 15.04.2011 31.12.2012 | 0 | 0.007 | 6.5 | 7.43 | 18.87 | 0.47 | 0 | 0.47 | 20.35 | 5.12.2010 | 19.34 | 97% | Boundary Wall Completed. | 40.63 | 0.98 | 8.98 | -7.43
Guest House - Two storey 1RCC frame work and slab has been completed & flooring work is complted except toilets and main entrance area and building likely to be completed upto 31.11.2013. House Type-I Two Stroey Work is completed and handed over to CIPET
5 | PTPS, Panipat
a | Construction of 126 nos houses of various category and 1 nos. service building for Unit No. 7 and 8 at Panipat Thermal Power Station at Panipat (M/s Allied) | 24.08 | 18.67 | 16.6 | 11.02.2010 | 11.05.2011 15.09.2011 | 0 | 0 | 9.395 | 6.21 | 2.53 | 0 | 0 | 0 | 19.05 |  | 18.14 |  | Cat-II 48 nos houses (double storey) Work completed. Handed over
Type III - 36 no houses (Double storey) Work completed. Handed over.
Type IV - 30 nos houses (Double Storey) Work completed and handed over.
Type V - 5 nos houses (single storey) Work completed. Handed over
Type VI - 3 nos houses (single storey) Work completed. Handed over
Type VII - 1 nos houses (single storey) Work completed. Handed over
Service Building (Four storey) 1The work of service building stands completed.The fixture of Fire fighting work is yet to be fixed that will be fixed at the time of handing over the building.Civil work / PH work and E.I work completed.
b | Providing air conditioning system in service buidilng for the unit no 7 and 8 in PTPS panipat | 0 | 0.9597 |  | 09.11.2011 |  | 0 | 0 | 0 | 0.44 | 0.41 | 0 | 0 | 0 | 0 |  | 0.84 |  | Both panel i.e motorized/ A.C panel has been enerized by the HPGCL.The Testing work is completed.
c | Providing one number 13 passenger elevator in service buiding for unit no. 7 & 8 in the campus of PTPS panipat | 0 | 0.16 | 0 | 03.02.2012 | 03.06.2012 | 0 | 0 | 0 | 0 | 0.14 | 0 | 0 | 0 | 0 |  | 0.14 |  | Testing work is in progress.
d | Providing electrical fixutres in the service buidling for unit No 7 and 8 in the campus of PTPS panipat | 0.24 | 0 | 0 | 15.02.2012 | 30.04.2012 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0 |  | 0.19 |  | Electric Panel has been energized by the HPGCL on 25.09.2013
e | Providing electrical panels in the service buidling for Unit No. 7 and 8 in the campus of PTPS panipat | 0.25 | 0 | 0 | 30.03.2012 | 15.05.2012 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0 | 0 | 0 |  | 0.18 |  | Electric Panel has been energized by the HPGCL on 25.09.2013.Testing of tube fittings/Fans has almost completed.
| TOTAL | 24.57 | 19.7897 | 16.6 |  |  |  |  | 9.395 | 6.65 | 3.45 | 0 | 0 | 0 | 20.46 |  | 19.49
6 | Construction of Girls hostel in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 7.49 | 4.8 |  | 17.08.2011 | 17.08.2012 | 0 | 0 | 0.01 | 0.83 | 2.62 | 0 | 0.1 | 0.1 | 4.37 |  | 4.16 |  | (A) Overallprogress Report Mess Block- Complete in all respect. i) Completed exceipt outer finishing work. Hostel Block Ist Storey Slab brick work completed,60% palster,60% Kota stone flooring ,80% trazzo tile flooring & 60% window shutter completed.60% wall tiles & flooring tiles completed remaining work is in progress. 2nd storey Slab laid , brick work,plaster & flooring completed and 60% door and window shutter completed remaing work is in progress. 3 storey Slab and brick work completed , 70% plaster and flooring completed and remaining work is in progress. 4th storey Slab & brick work completed and 90% plaster & 80% flooring completed Remaining work is in progress. |  |  | 0.93 | -1.75
7 | Construction of Teaching Block (Phase I) in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 9.39 | 8.83 |  | 05.10.2011 | 05.10.2012 | 0 | 0 | 0 | 0.1 | 3.08 | 0 | 0.53 | 0.53 | 4.72 |  | 4.5 |  | Overall Progtess Report Ist Storey 1. 98% foundaton and plinth completed and balance work is in progress. 2. 95% R.C.C Slab,75% brick work of Super Structure completed and balance work is in progress. 3. 98% brick work in foundation & plinth completed and balance work is in progress 4.65% cement plaster completed. 65% Kota stone flooring completed. i) 70% RCC slab slab 65% brick work & joinery work completed. ii) 50% Kota stone flooring laid 3rd storey i)65% slab laid and 65% brick work completed. ii) 65% brick work completed and balance work is in progress. 4th storey 65% slab laid and 65% brick work completed. 4th storey 65% slab laid and 65% brick work completed. B) Progress upto Expansion Joint. Complete in all respect. ii) 2nd storey : All slab inluding staircase completed.70% inner palster work,brick work,Kota flooring & Joinery work completed.Sanitary fitting and outer and inner fininshing work is in progress. iii) 3rd Storey Slab laid & Brick work completed .Plaster work in progress. 4th Storey Slab and brick work completed and flooring work is in progress.
8 | Construction of internal road in Post Graduate Regional Centre for Kurukshetra University at Jind in Jind district. | 0.94 |  |  | 16.10.2013 | 15.02.2014 | 0 | 0 | 0 | 0 | 0 | 44.04 | 0 | 44.04 | 0 |  | 44.04 |  | Earthwork, stone aggregate G-I,G-II & G-III completed except main gate portion.
9 | Construction of Academic staff hostel, Scholar Hostel Hospitality and Hospital administration, Administrative block and degree college at BPSMV Khanpur Kalan. | 7.68 | 8.69 |  | 31.08.2011 | 31.08.2012 | 0 | 0 | 0 | 1.59 | 3.51 | 0.26 | 1.57 | 1.83 | 4.9 |  | 4.67 |  | Administrative Block (DOUBLE STOREY) :- 100% column in first storey upto slab level completed. 80% area of ground floor slab laid and in reaminig 20% area shutteirng, reinforcement is in progress. Brick work, plaster work, electricity work of ground f
B.Sc labs for Hospitality / Hotel Administration (DOUBLE STOREY):- 100% column of second storey is completed. Shuttering of slab is completed and reinforcmeent is in progress for second storey slab.
Administrative Block: (Double storey): All slab laid except machine room ,75%vitrified flooring ,50% aluminium joinery,70% wall putty,50% false ceiling completed and balance work wooden flooring ,railing and baroda green flooring,sanitary work,electrical
Academic Staff Hostel (DOUBLE STOREY) :- 1 Footing work completed and filling of earth is in progress.Casting of coloumns for ground floor is in progress.
Hostel for Degree college (SINGLE STOREY):- All slab Brick work and plaster work completed,Joinery and flooring work is in progress..
9 | Construction of additional block at district Hospital Panipat | 20 | - | [15 empty] | Detailed estimate /DNIT under preparation.
10 | Construction of additional block at district Hospital Rewari | 20 | 5.49 |  | 23.11.12 | 22.02.2014 | - | - | - | - | 1.02 | 0.92 | 0.19 | 0.92 | 2.03 |  | 1.94 |  | LHS & RHS portion ground floor slab work complete. First Floor slab shuttering work in progress.
11 | Construction of additional block at district Hospital Dadri | 10 | 6.33 |  | 19.04.2012 | 18.10.2013 | - | - | - | - | 1.98 | 1.25 | 0.6 | 1.85 | 4.02 |  | 3.83 |  | RCC work in foundation 98% complete. Ground Floor slab 80% complete Ground Floor brick work 65% completed. Ist Floor slab 65% completed. Ist Floor level brick work 30% completed. further work in progress. Intially work delayed on account of stay order by
131.901